## Instructions
RISK MANAGEMENT LOG
Column | Instructions For Completing This Document
Complete the Project Name, NC, Project Manager Name, and Project Description fields
For each risk identified, complete the following:
A | ID: A unique ID number used to identify the risk in the risk tracking log.
B | Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
C | Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
D | Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue.
E | Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
F | Risk Description: This column should be populated with a description of the risk.
G | Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
H | Risk Area: This column should be populated with the appropriate risk area.
I | Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
J | Trigger: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
K | Risk Response Strategy: This column should be populated with the preferred risk response strategy.
L | Response Strategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
M | Contingency Plan: This column should be populated with a description of the risk contingency plan.
Column | Instructions For Changing the Contents of Drop-Down Menus
C, D, H | Highlight the cell of which you wish to change the content of the drop down menu. From the file menu click "Data" -> "Validation" and change the content of the source field
Column | Instructions For Filtering Data
Any | Highlight the header of the cell you wish to filter data on From the file menu click "Date" -> "Filter" ->"Auto Filter" Then select your filter criteria from the drop down menu that appears on your header cell

## Risk_Tracking_Log
RISK MANAGEMENT LOG
Project Name: |  |  | 303 – DPI: IoTa Timeseries Database
National Center: |  |  | DPI via CSU
Project Members |  |  | Callum, Sara, Zak, Rishabh
Project Description: |  |  | Time Series Database implementation for DPI IoTa Project
ID | Current Status | Risk Impact | Probability of Occurrence | Risk Map | Risk Description | Project Impact | Risk Area | Symptoms | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan
0 | Closed | High | Medium | Closed | Remote Team with loose bindings: Team members are all remote, have never met, are not bound by contract/employment. | If one or more members fail to achieve set goals, fail to adequately communicate, bail out of subject, fail to meet group expectation, then the project could spiral quickly and may fail completely | Schedule, Project Management, Overall Project Failure | One or more members has not communicated or attended pre arranged meetings per team expectation, largely in regard to assigned tasks, time management, feedback, team meetings, input | One or more members has failed to: [1] attend a meeting, [2] communicate with the team, [3] provide feedback as laid out in the agreed teamcharter | Avoidance | [1] Enforce team charter, [2] Aim to remain proactive with communication | [1] Enforce team charter: notify lecturer/kick team member [2] Re-evaluate where the project stands in terms of feasibility
1 | Open | Medium | Medium | Yellow | Skills and Knowledge: Our knowledge is limited in both management side i.e planning and designing, along with technical skills such as python, linux, docker, api | Project quality may suffer, the architecture may be insuffient, NFR and FR may not be met. If NFR is not being met then generally it is a design issue which can take far more time to resolve versus FR. | Schedule, Feasibility, Reliability of Systems, Project Management, Security, Overall Project Failure | Functional and/or Non Functional requiments are not being met, estimated completion times are blown out, app does not appear to be robust or is error prone, codebase size may be unproportionate with implemented system features | When there are any multiple of these: [1] error prone apps, [2] apps are not robust, [3] security is compromised, [4] codebase becomes unnessarily complex | Avoidance | [1] Increase static code review number, [2] Increase automated testing/unit tests, [3] Increase extra learning to catch up with required knowledge | [1] Enforce required learning as work items in iterations [2] Assign buddy roles based on strengths to ensure tasks are completed to standard, are complete and functioning per project guidelines
2 | Closed | Medium | Medium | Closed | Complexity of the project: Although considered a small project, there is some complexity here, there are multiple database technologies (postgres, timeseries), there are multiple message formats, multiple devices, multiple 3rd party platforms/technologies (RabbitMQ, TTN, docker/docker-compose, python, bash, git). There is certainly many design aspects that would need to be considered | Project may fail to meet NFR, although FR are probably fine. Project may fail to be easily expandable in future. If NFR is not being met then generally it is a design issue which can take far more time to resolve versus FR. | Schedule, Life-cycle Costs, Technology, Security | NFR are not being met, failing to meet tasks on time, application is error prone/buggy | [1] If previous implemented sections start to intefere or need modification in order to prevent current/future sections, [2] Application is not stable | Avoidance | There is no time to lose in redesign, so we need to avoid this risk by [1] designing and researching thoroughly before we start implementing the project. [2] Testing may help with improving or identifying NFR risks such as robustness, performance, security | [1] Enforce more time for project planning, [2] Explore extra meetings to ensure well thought out and cohesive design, [3] Seek outside help so that project does not fail
3 | Closed | Low | Medium | Closed | Project scope remains a little unclear, there has been some conflcting information or lacking information regarding certain project details. Examples are documentation uses 'the database' implying it exists but has maybe not been implemented yet, however from meeting it seems there is no timeseries database, nor has one been selected to be implemented, document mentions that we will be given a container to run it in, but also it must be able to be added to existing docker compose stack; this is unclear | May spend some time learning/thinking about the project in slightly incorrect ways, or ultimately trying to implement it different as stakeholders would like | Schedule, Initial Costs | FR and NFR are being implemented/designed in a way contrary to how the stakeholders would like | [1] Team are unable to determine particulars for certain aspects, [2] Team are confused in relation to certain particulars, [3] Team have spent some time focusing on wrong 'goals' | Mitigation | The goal is to mitigate this aspect with strong communication- [1] Gain confirmation from stakeholders, [2] Generate a list of issues team are having and bring it up in weekly meeting with stakeholders | [1] Send documentation early to stakeholders for review, [2] Perform 'response strategy' with more intent
4 | Closed | Medium | Low | Closed | As we are a uni group and our contributions are to be equal, we have not assigned a team leader. It may be considered easier for the team to fail to enforce the team charter | Schedule may blow out due to spending more time being bureaucratic rather than focusing on goals. Team may falter on original discussed goals or expectations due to lack of leadership | Project Management, Schedule | Organised meetings and other communication start to draw out or even fail to obtain an outcome. Team charter violations are not enforced. 'In Fighting' | [1] Meetings start to fail to resolve issues, [2] Team are unable to agree on outcomes | Mitigation | The goal is to mitigate this by following the team charter that handles how we will make decisions. If this starts to cause issues, we would need to implement a strict time policy for making decision i.e 24h | [1] Assign a team leader
5 | Open | Low | Medium | Green | Lacked experience: There are to be many easy to avoid pitfalls our team may fall into due to lack of experience, these can cause delays in producing a product. | Schedule may blow out due to a high degree of learning as we go | Schedule, Initial Costs, Security | Time to implement increases more than we'd expect, or aspects require redesign at later stages/too many times | [1] Team are unable to understand or determine possible course of actions, [2] Codebase has a high degree of levels, poor coding practice, not meeting best standards for particular implementations, [3] Team are getting stuck on seemingly trivial tasks, [4] Team are required to rework completed sections | Acceptance | [1] Allow extra time to implement goals generally in the case of a buffer between actual due dates [2] Spend extra time outside of project gaining experience in key technologies | [1] Allow even more time to implement and research features
6 | Closed | Low | Low | Closed | Differing Development Environments: Most of the team predominantly use windows, and this project can be considered linux based as it must be run on linux, vm, or windows linux subsystem. This means that team must learn to use a different development environment that they are used to, and likely each use a different one from each other | Schedule may blow out a small amount due to extra minor issues. | Schedule, Technology, Initial Costs, Project Resources | Occurance of issues that would not have existed if we all shared an identical environment; Occurance of issues that exist due to lack of experience with development environment or such issues take considerable time to resolve. It becomes difficult for team members to offer assistance due to differing environments | [1] Team members are getting stuck on environmental aspects, [2] Team are getting stuck on different aspects when it comes to environment/development aspect | Acceptance | [1] Aim to minimise differences as much as possible, for instance using the same docker containers for running extra apps | [1] Enforce some environmental constraints i.e same operating system, software versions
7 | Closed | Low | Medium | Closed | Microservice architecture: The current architecture for the platform uses microservices, our section will need to integrate well with existing services which may increase the chances of issues occuring | Extra debugging will likely be required in order to resolve foreseeable integration issues with the current platform. | Schedule | When testing and deploying issues arise from the communication between services | [1] When there are considerable issues integrating with existing pieces | Acceptance | [1] Rethink the design on how we integrate the new parts with existing parts. [2] add extra unit tests to try catch issues earlier | [1] Impletement a strict debugging and testing protocol
8 | Closed | Low | Low | Closed | Extra Tasks: During the initial meeting, extra features were mentioned, and can be taken on if the team likes, this would take away time spent on the main project and therefore add risk of delay | Schedule may be impacted | Schedule | Extra features are being done before the main feature set. Possible failure to complete after committing to extra tasks. | [1] The main feature set falls behind whilst the extra feature set is still being worked on. [2] Underestimation of either the extra tasks or the main tasks. | Mitigation | [1] Stop working on extra features until the project has caught up. [2] Scale back scope within extra tasks. | [1] Increase time spent in completion of tasks. [2] Delay completion into transition phase.
9 | Open | High | Medium | Red | Time Series Database: Picking a TSDB and then implementing it are rather risky, if we pick the wrong TSDB then the whole project is at risk, if we fail to implement it properly then FR and NFR are at risk | Although the project has a small performance requirement, a database implementation can be difficult to change down the line so It must be done correctly. This is both for inital design choices and implementation | Security, Life-cycle Costs, Data Information, Technology | There are issues with schema, retrieval of data, storage of data or access to data | [1] Unable to access, retrieve or store the required information to or from the database [2] Data can be accessed or modified in unexpected ways | Mitigation | [1] Analyse design of database and it's implementation and research alternate ways to reach goals [2] Deeper research and testing of TSDB options | [1] Re-evaluate design and selected database, [2] Design ways to circumvent faced issues using existing implementation, [3] Seek external help
10 | Closed | Low | Low | Closed | API implementation: One key FR is api for the app, this will need to be implemented in a secure, efficient way, likely through FastAPI as existing ecosystem use this. | If the API is not robust, secure and efficient then it will fail to meet FR/NFR | Reliability of Systems, Security, Privacy | Unable to access the API or perform the tasks via the API. The API can be accessed or used by unauthorised users | [1] The API does not perform as expected, this can be in ways of access, received data, stability | Mitigation | [1] Analyse implementation of API elements and redesign to better accomplish goals. | [1] Allocate extra time for learning, design and implementation of API related features, [2] Seek external help
11 | Closed | Low | Low | Closed | Message parsing: Key FR is to parse incoming messages or messages from and two multiple databases. | It is possible for errors in implementation to slip by causing issues with edge cases or newer messages in the future. | Reliabilty of Systems, Data Information, Technology | During testing, data enterered or passed though to other systems is incorrect, inconsistent, or is changed beyond expectation (i.e int to str) | [1] Data is missing [2] Data is in the wrong format or type [2] Data is incorrect or changed between message formats | Mitigation | [1] Better determine incoming and outgoing message requirements and alter implementation of the parsing to suit. | [1] Seek aid from stakeholders
12 | Open | Medium | Low | Green | Addtional Requirement: Initially we were working with the idea that we must build a database with persistent logical IDs that have a physical ID which can change. This has now changed, and they both should be replaceable. | Database can no longer use logical ID as a primary key, the structure may require an addtional ID for each pairing of physical and logical IDs. Output service will likely need logic to handle cases where this changes. | Data/Information | Failure to update these pairings will result in queries being incorrect. Will require further additons to development time which may strain the schedule. | [1] Lacking consideration for logic changes, and potential issues that may arise. [2] Existing extra tasks may result in further issue in time managment. | Avoidance | [1] Make consideration for this in database design avoid issues later, otherwise: [2] Allocate additional time to deal with the ill-considered logic issues. | [1] Adjust schedule where possible and push back additional tasks further.

## Changelog
Changelog for this Document:
Date: | Change:
15/05/23:
- Increased probability of “Lacked Experience” to medium, as we have found some tasks more complex than assumed during elaboration.
- Changed “Extra Tasks” risk back to open as it’s currently in consideration once again (due to expected workload for multiple DB testing being reduced).
- Added extra symptom, triggers, response strategy for “Extra Tasks”.
19/05/23:
- Added additional risk regarding new requirement on physical and logical IDs.
- Reduced probability of “microservice architecture” and “skills and knowledge” risk to medium, due to already implementing an aspect of our service into this architecture.
29/05/23:
- Closed extra tasks again, as we discussed that technically its no longer extra, and we've accepted it as part of the project plan which has the same risks as any other task.
- Closed API implementation, as discussed with team, shouldn't be a worry as we've implemented a basic setup, and there is existing DPI API we can emulate/modify
- Closed Remote team issue, mainly in place for the sake of being unsure if team would as is, but at this point its clear we're good.

## DropDown_Elements (hidden)
Risk Area
Schedule
Initial Costs
Life-cycle Costs
Technical Obsolescence
Feasibility
Reliability of Systems
Dependencies/Interoperability
Surety Considerations
Future Procurements
Project Management
Overall Project Failure
Organizational/Change Management
Business
Data/Information
Technology
Strategic
Security
Privacy
Project Resources